## Sowrasree
Agile Task Board
Assigned To: | Sowrasree Banerje
Use Case: | Use Case 3
Team: | Team B
Task | Actual No. of Hours Expected | Actual No. of Hours
Distributor
Create SQL Server table named "Distributor" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5
UI - Create Distributor using Angular for CRUD operations | 2 | 2 | issues with array, objects and character casing
UI - Create Angular Component & Template for "Distributor Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Add Distributor Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for " Update Distributor" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Distributor" using Bootstrap & Angular | 1 | 2
Task | Actual No. of Hours Expected | Actual No. of Hours
DistributorAddress
Create SQL Server table named "DistributorAddress" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 1 | 1
UI - Create DistributorAddress using Angular for CRUD operations | 1 | 1.5 | issues with array, objects and character casing
UI - Create Angular Component & Template for "Distributor Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Add Distributor Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for " Update Distributor" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Distributor" using Bootstrap & Angular | 1 | 1

## Rohit
Agile Task Board
Assigned To: | Rohit Kumar
Use Case: | Use Case 2
Team: | Team D
Task | Actual No. of Hours Expected | Actual No. of Hours
Distributor
Create SQL Server table named "RawMaterial" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 3
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5 | issues with array and routing
UI - Create Distributor using Angular for CRUD operations | 2 | 2.5
UI - Create Angular Component & Template for "Rawmaterial Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Add RawMaterial" Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for " Update RawMaterial" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete RawMaterial" using Bootstrap & Angular | 1 | 2
Task | Actual No. of Hours Expected | Actual No. of Hours
DistributorAddress
Create SQL Server table named "Product" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1.5
Prepare Test Cases using Excel for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 1 | 1.5
UI - Create DistributorAddress using Angular for CRUD operations | 1 | 1 | issues with array and routing
UI - Create Angular Component & Template for "Product Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Add Product Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for " Update Product Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Product page" using Bootstrap & Angular | 1 | 1.5

## Maski
Agile Task Board
Agile Task Board | Maski Saijahnavi
Use Case: | Use Case 3
Team: | Team D
Task | Actual No. of Hours Expected | Actual No. of Hours
ProductOrder
Create SQL Server table named "ProductOrders" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2.5
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5 | issues with array and routing
UI - Create OrdersService using Angular for CRUD operations | 2 | 2.5
UI - Create Angular Component & Template for "Product Orders Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Create Product Order Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Edit Order Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Delete Order Page" using Bootstrap & Angular | 1 | 1.5
Task | Actual No. of Hours Expected | Actual No. of Hours
ProductOrderDetails
Create SQL Server table named "ProductOrderDetails" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2 | issues with array and routing
UI - Create OrdersService using Angular for CRUD operations | 1 | 1.5
UI - Create Angular Component & Template for "Product Orders Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Create Product Order Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Edit Order Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Order Page" using Bootstrap & Angular | 1 | 1

## Ritwik
Agile Task Board
Agile Task Board | Ritwik Sinha
Use Case: | Use Case 2
Team: | Team D
Sprint 7- Dotnet with cloud Batch Sprint Date- 4th Nov, 2019 to 15th Nov,2019 Topic- Deploying ASP project on Azure with two operations
Task | Actual No. of Hours Expected | Actual No. of Hours | Reason | Details
Inventory
Create WebApi Controller in Azure (04 to 06 nov 2019) | 1 | 2 | Learnt the Basic coding concepts about web api and and utilized on code. | Created webApi Controller and web Api configuration file containing object of Business layer with the required method.
Create HTML page using CSS and Bootstrap ( 06 nov 2019) | 2 | 2 | On time | Created a HTML page displaying records of all the orders or entities created.
Consuming WebApi through AJAX ( 12-13 nov 2019) | 1 | 1 | On time | Consumed WebApi through AJAX method To display Entities list.
Put up Database scripts on Azure Database SQL server ( 12 nov 2019) | 1 | 1 | On time | database scripts were executed and then put up on the azure database sql server.
Deploy the WebApi project on Azure ( 14 Nov 2019) | 2 | 2.5 | As Azure is the new topic, It took time to learn the architecture. | It was a total new and useful concept to deploy our application on azure and learnt about the advantages.
Correction in MVC project and introduction to Azure and virtual machines.( 04 nov 2019) | 2 | 2 | On time | Correction in validation was done.
creation of app service( 07 nov 2019) | 2 | 2.5 | As it was a new topic it took time to create the App service. | Creation of App service was performed , it took a bit time as we were new to technology and it is chargeable.
creation of Active directory and learnt to monitor (08 nov 2019) | 2 | 2.5 | Time was utilized to create a resource and active directory. | created active directory to observe monitoring of the application and server, then monitor the load.
Creation of logic and queue using Logic app ( 11 nov 2019) | 1 | 1.5 | Time was taken to create a storage account and then process. | Creation of Storage account was performed , it took a bit time as we were new to technology and it is chargeable.
Creation of virtual machine ( 08 nov 2019) | 2 | 2 | On time | Created virtual machine and and observed that it utilizes a lot of memory.
Creation of function through azure function app ( 07 nov 2019) | 1 | 1 | On time | Creation of Function App was performed , it took a bit time as we were new to technology and it is chargeable.
Demo for load Balancing and controlling traffic ( 07 nov 2019) | 2 | 2 | On time | Since a lot users can work on a single server at a time , load balancer needs to be used.
Creation of storage account ( 07 nov 2019) | 1.5 | 2 | As it was a new topic it took time to create the storage account | Creation of Storage account was performed , it took a bit time as we were new to technology and it is chargeable.
Using Function to do CRUD operations on SQL database ( 06 nov 2019) | 1 | 1 | On time | Crud operations were carried on the sql database and stored procedures.
Creation of Web Cognitive Services ( 06 nov 2019) | 1 | 1 | On time | Web cognitive services were created.
| Sum- 22.5 hrs | Sum- 26 hrs
Note on A24: Sinha, Ritwik:

## Pushpraj
Agile Task Board
Assigned To: | Pushpraj Kaushik
Use Case: | Use Case 1
Team: | Team D
Task | Actual No. of Hours Expected | Actual No. of Hours
Supplier
Create SQL Server table named "Supplier" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 3
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5 | issues with array, routing and character casing
UI - Create Supplier using Angular for CRUD operations | 2 | 2.5
UI - Create Angular Component & Template for "Supplier Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Add Supplier Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for " Update Supplier" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Supplier" using Bootstrap & Angular | 1 | 2
Task | Actual No. of Hours Expected | Actual No. of Hours
SupplierAddress
Create SQL Server table named "SupplierAddress" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2
UI - Create SupplierAddress using Angular for CRUD operations | 1 | 1 | issues with array, routing and character casing
UI - Create Angular Component & Template for "Supplier Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Add Supplier Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for " Update Supplier" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Delete Supplier" using Bootstrap & Angular | 1 | 1.5