## Sowrasree
Agile Task Board
Assigned To: | Sowrasree Banerje
Use Case: | Use Case 3
Team: | Team B
Task | Actual No. of Hours Expected | Actual No. of Hours
Distributor
Create SQL Server table named "Distributor" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5
UI - Create Distributor using Angular for CRUD operations | 2 | 2 | issues with array, objects and character casing
UI - Create Angular Component & Template for "Distributor Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Add Distributor Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for " Update Distributor" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Distributor" using Bootstrap & Angular | 1 | 2
Task | Actual No. of Hours Expected | Actual No. of Hours
DistributorAddress
Create SQL Server table named "DistributorAddress" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 1 | 1
UI - Create DistributorAddress using Angular for CRUD operations | 1 | 1.5 | issues with array, objects and character casing
UI - Create Angular Component & Template for "Distributor Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Add Distributor Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for " Update Distributor" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Distributor" using Bootstrap & Angular | 1 | 1

## Rohit
Agile Task Board
Assigned To: | Rohit Kumar
Use Case: | Use Case 2
Team: | Team D
Task | Actual No. of Hours Expected | Actual No. of Hours
Distributor
Create SQL Server table named "RawMaterial" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 3
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5 | issues with array and routing
UI - Create Distributor using Angular for CRUD operations | 2 | 2.5
UI - Create Angular Component & Template for "Rawmaterial Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Add RawMaterial" Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for " Update RawMaterial" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete RawMaterial" using Bootstrap & Angular | 1 | 2
Task | Actual No. of Hours Expected | Actual No. of Hours
DistributorAddress
Create SQL Server table named "Product" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1.5
Prepare Test Cases using Excel for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 1 | 1.5
UI - Create DistributorAddress using Angular for CRUD operations | 1 | 1 | issues with array and routing
UI - Create Angular Component & Template for "Product Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Add Product Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for " Update Product Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Product page" using Bootstrap & Angular | 1 | 1.5

## Maski
Agile Task Board
Agile Task Board | Maski Saijahnavi
Use Case: | Use Case 3
Team: | Team D
Task | Actual No. of Hours Expected | Actual No. of Hours
ProductOrder
Create SQL Server table named "ProductOrders" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 2.5
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5 | issues with array and routing
UI - Create OrdersService using Angular for CRUD operations | 2 | 2.5
UI - Create Angular Component & Template for "Product Orders Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Create Product Order Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Edit Order Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Delete Order Page" using Bootstrap & Angular | 1 | 1.5
Task | Actual No. of Hours Expected | Actual No. of Hours
ProductOrderDetails
Create SQL Server table named "ProductOrderDetails" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2 | issues with array and routing
UI - Create OrdersService using Angular for CRUD operations | 1 | 1.5
UI - Create Angular Component & Template for "Product Orders Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Create Product Order Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Edit Order Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Order Page" using Bootstrap & Angular | 1 | 1

## Ritwik
Agile Task Board
Agile Task Board | Ritwik Sinha
Use Case: | Use Case 2
Team: | Team D
Sprint 8- Dotnet with cloud Batch Sprint Duration- 15th Nov, 2019 to 22th Nov,2019 Topic- Deploying MVC project on Azure with CICD through Dev-ops
Task | Actual No. of Hours Expected | Actual No. of Hours | Reason | Details
Inventory
Create WebApi Controller ( Solution) in Azure ( 16 nov 2019) | 1 | 2 | Learnt the Basic coding concepts about web api and and utilized on code. | Created webApi Controller and web Api configuration file containing object of Business layer with the required method.
Create the MVC project with Model view Controller with validation( 18 nov 2019) | 2 | 2 | On time | Created a MVC project Model view Controller with validation .
Consuming WebApi through MVC ( 21 nov 2019) | 1 | 1 | On time | Consumed WebApi through MVC method On all the CRUD operations.
Put up Database scripts on Azure Database SQL server ( 16 nov 2019) | 1 | 1 | On time | database scripts were executed and then put up on the azure database sql server.
Deploy the MVC project on Azure ( 21 Nov 2019) | 2 | 2.5 | As Azure is the difficult topic, It took time to learn the architecture. | It was a total new and useful concept to deploy our application on azure and learnt about the advantages.
Connect MVC project with Web Api( 20 nov 2019) | 2 | 2 | On time | Connection of web api and MVC was done and the project was running on local host.
learning of Dev-OPs( 20 nov 2019) | 2 | 2.5 | As it was a new topic it took time to learn Dev - ops. | Dev-ops were very essential for continuous integration.
Analysis of PLP documents ( 19 nov 2019) | 2 | 2 | On time | PLP documents were Analysed and we went through the urs and other documents.
Revision Of Azure Concepts ( 19 nov 2019) | 1 | 1 | On time | Azure Concepts were Revisied red we went through the urs red other Concepts.
Learning the Agile and Scrum model ( 18 nov 2019) | 3 | 3 | On time | learnt about the basics of agile and scrum model
Creating Various PLP documents as URS, PRODUCT BACKLOG etc( 20 nov 2019) | 4 | 5 | As we needed to create 5 documents, so it took time. | Various documents were created Like urs etc.
| Sum - 21 hours | Sum - 22 hours
| Sum- 22.5 hrs | Sum- 26 hrs
Note on A23: Sinha, Ritwik:

## Pushpraj
Agile Task Board
Assigned To: | Pushpraj Kaushik
Use Case: | Use Case 1
Team: | Team D
Task | Actual No. of Hours Expected | Actual No. of Hours
Supplier
Create SQL Server table named "Supplier" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 2 | 3
Prepare Test Cases using Excel for all CRUD operations | 1 | 1.5
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2.5 | issues with array, routing and character casing
UI - Create Supplier using Angular for CRUD operations | 2 | 2.5
UI - Create Angular Component & Template for "Supplier Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Add Supplier Page" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for " Update Supplier" using Bootstrap & Angular | 2 | 2.5
UI - Create Angular Component & Template for "Delete Supplier" using Bootstrap & Angular | 1 | 2
Task | Actual No. of Hours Expected | Actual No. of Hours
SupplierAddress
Create SQL Server table named "SupplierAddress" | 0.5 | 0.5
Create Stored Procedures for all CRUD Operations | 1 | 1
Prepare Test Cases using Excel for all CRUD operations | 1 | 1
Prepare Test Cases using MSUnit test cases for all CRUD operations | 2 | 2
UI - Create SupplierAddress using Angular for CRUD operations | 1 | 1 | issues with array, routing and character casing
UI - Create Angular Component & Template for "Supplier Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Add Supplier Page" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for " Update Supplier" using Bootstrap & Angular | 2 | 2
UI - Create Angular Component & Template for "Delete Supplier" using Bootstrap & Angular | 1 | 1.5