## Sheet1
Sprint 8- Dotnet with cloud Batch Sprint Duration- 15th Nov, 2019 to 22th Nov,2019 Topic- Deploying MVC project on Azure with CICD through Dev-ops
Sprint Start date | 2019-05-11 | Day | Forecast | Target | Actual
Sprint End Date | 11-21-2019 | 0 | 315 | 450 | 450
Working Days | 15 | 1 | 294 | 420 | 420
Team Size | 5 | 2 | 273 | 390 | 410
Work Hours per day | 6 | 3 | 252 | 360 | 390
total Available hours | 450 | 4 | 231 | 330 | 345
Average Daily Available hours | 30 | 5 | 210 | 300 | 310
Average productivity | 70 | 6 | 189 | 270 | 295
productive hours | 315 | 7 | 168 | 240 | 240
Avg Daily productive hours | 21 | 8 | 147 | 210 | 220
|  | 9 | 126 | 180 | 170
|  | 10 | 105 | 150 | 160
|  | 11 | 84 | 120 | 150
|  | 12 | 63 | 90 | 90
|  | 13 | 42 | 60 | 60
|  | 14 | 21 | 30 | 45
|  | 15 | 0 | 0 | 0