## Sowrasree
Agile Task Board
Assigned To: | Sowrasree Banerje
Use Case: | Use Case 3
Team: | Team B
Task | Actual No. of Hours Expected | Actual No. of Hours | Reason | Details
Inventory
Create WebApi Controller ( Solution) in Azure ( 16 nov 2019) | 1 | 2 | Learnt the Basic coding concepts about web api and and utilized on code. | Created webApi Controller and web Api configuration file containing object of Business layer with the required method.
Create the MVC project with Model view Controller with validation( 18 nov 2019) | 2 | 2 | On time | Created a MVC project Model view Controller with validation .
Consuming WebApi through MVC ( 21 nov 2019) | 1 | 1 | On time | Consumed WebApi through MVC method On all the CRUD operations.
Put up Database scripts on Azure Database SQL server ( 16 nov 2019) | 1 | 1 | On time | database scripts were executed and then put up on the azure database sql server.
Deploy the MVC project on Azure ( 21 Nov 2019) | 2 | 2.5 | As Azure is the difficult topic, It took time to learn the architecture. | It was a total new and useful concept to deploy our application on azure and learnt about the advantages.
Connect MVC project with Web Api( 20 nov 2019) | 2 | 2 | On time | Connection of web api and MVC was done and the project was running on local host.
learning of Dev-OPs( 20 nov 2019) | 2 | 2.5 | As it was a new topic it took time to learn Dev - ops. | Dev-ops were very essential for continuous integration.
Analysis of PLP documents ( 19 nov 2019) | 2 | 2 | On time | PLP documents were Analysed and we went through the urs and other documents.
Revision Of Azure Concepts ( 19 nov 2019) | 1 | 1 | On time | Azure Concepts were Revisied red we went through the urs red other Concepts.
Learning the Agile and Scrum model ( 18 nov 2019) | 3 | 3 | On time | learnt about the basics of agile and scrum model
Creating Various PLP documents as URS, PRODUCT BACKLOG etc( 20 nov 2019) | 4 | 5 | As we needed to create 5 documents, so it took time. | Various documents were created Like urs etc.

## Rohit
Agile Task Board
Assigned To: | Rohit Kumar
Use Case: | Use Case 2
Team: | Team D
Task | Actual No. of Hours Expected | Actual No. of Hours | Reason | Details
Inventory
Create WebApi Controller ( Solution) in Azure ( 16 nov 2019) | 1 | 2 | Learnt the Basic coding concepts about web api and and utilized on code. | Created webApi Controller and web Api configuration file containing object of Business layer with the required method.
Create the MVC project with Model view Controller with validation( 18 nov 2019) | 2 | 2 | On time | Created a MVC project Model view Controller with validation .
Consuming WebApi through MVC ( 21 nov 2019) | 1 | 1 | On time | Consumed WebApi through MVC method On all the CRUD operations.
Put up Database scripts on Azure Database SQL server ( 16 nov 2019) | 1 | 1 | On time | database scripts were executed and then put up on the azure database sql server.
Deploy the MVC project on Azure ( 21 Nov 2019) | 2 | 2.5 | As Azure is the difficult topic, It took time to learn the architecture. | It was a total new and useful concept to deploy our application on azure and learnt about the advantages.
Connect MVC project with Web Api( 20 nov 2019) | 2 | 2 | On time | Connection of web api and MVC was done and the project was running on local host.
learning of Dev-OPs( 20 nov 2019) | 2 | 2.5 | As it was a new topic it took time to learn Dev - ops. | Dev-ops were very essential for continuous integration.
Analysis of PLP documents ( 19 nov 2019) | 2 | 2 | On time | PLP documents were Analysed and we went through the urs and other documents.
Revision Of Azure Concepts ( 19 nov 2019) | 1 | 1 | On time | Azure Concepts were Revisied red we went through the urs red other Concepts.
Learning the Agile and Scrum model ( 18 nov 2019) | 3 | 3 | On time | learnt about the basics of agile and scrum model
Creating Various PLP documents as URS, PRODUCT BACKLOG etc( 20 nov 2019) | 4 | 5 | As we needed to create 5 documents, so it took time. | Various documents were created Like urs etc.

## Maski
Agile Task Board
Agile Task Board | Maski Saijahnavi
Use Case: | Use Case 3
Team: | Team D
Task | Actual No. of Hours Expected | Actual No. of Hours | Reason | Details
Inventory
Create WebApi Controller ( Solution) in Azure ( 16 nov 2019) | 1 | 2 | Learnt the Basic coding concepts about web api and and utilized on code. | Created webApi Controller and web Api configuration file containing object of Business layer with the required method.
Create the MVC project with Model view Controller with validation( 18 nov 2019) | 2 | 2 | On time | Created a MVC project Model view Controller with validation .
Consuming WebApi through MVC ( 21 nov 2019) | 1 | 1 | On time | Consumed WebApi through MVC method On all the CRUD operations.
Put up Database scripts on Azure Database SQL server ( 16 nov 2019) | 1 | 1 | On time | database scripts were executed and then put up on the azure database sql server.
Deploy the MVC project on Azure ( 21 Nov 2019) | 2 | 2.5 | As Azure is the difficult topic, It took time to learn the architecture. | It was a total new and useful concept to deploy our application on azure and learnt about the advantages.
Connect MVC project with Web Api( 20 nov 2019) | 2 | 2 | On time | Connection of web api and MVC was done and the project was running on local host.
learning of Dev-OPs( 20 nov 2019) | 2 | 2.5 | As it was a new topic it took time to learn Dev - ops. | Dev-ops were very essential for continuous integration.
Analysis of PLP documents ( 19 nov 2019) | 2 | 2 | On time | PLP documents were Analysed and we went through the urs and other documents.
Revision Of Azure Concepts ( 19 nov 2019) | 1 | 1 | On time | Azure Concepts were Revisied red we went through the urs red other Concepts.
Learning the Agile and Scrum model ( 18 nov 2019) | 3 | 3 | On time | learnt about the basics of agile and scrum model
Creating Various PLP documents as URS, PRODUCT BACKLOG etc( 20 nov 2019) | 4 | 5 | As we needed to create 5 documents, so it took time. | Various documents were created Like urs etc.

## Ritwik
Agile Task Board
Agile Task Board | Ritwik Sinha
Use Case: | Use Case 2
Team: | Team D
Sprint 8- Dotnet with cloud Batch Sprint Duration- 15th Nov, 2019 to 22th Nov,2019 Topic- Deploying MVC project on Azure with CICD through Dev-ops
Task | Actual No. of Hours Expected | Actual No. of Hours | Reason | Details
Inventory
Create WebApi Controller ( Solution) in Azure ( 16 nov 2019) | 1 | 2 | Learnt the Basic coding concepts about web api and and utilized on code. | Created webApi Controller and web Api configuration file containing object of Business layer with the required method.
Create the MVC project with Model view Controller with validation( 18 nov 2019) | 2 | 2 | On time | Created a MVC project Model view Controller with validation .
Consuming WebApi through MVC ( 21 nov 2019) | 1 | 1 | On time | Consumed WebApi through MVC method On all the CRUD operations.
Put up Database scripts on Azure Database SQL server ( 16 nov 2019) | 1 | 1 | On time | database scripts were executed and then put up on the azure database sql server.
Deploy the MVC project on Azure ( 21 Nov 2019) | 2 | 2.5 | As Azure is the difficult topic, It took time to learn the architecture. | It was a total new and useful concept to deploy our application on azure and learnt about the advantages.
Connect MVC project with Web Api( 20 nov 2019) | 2 | 2 | On time | Connection of web api and MVC was done and the project was running on local host.
learning of Dev-OPs( 20 nov 2019) | 2 | 2.5 | As it was a new topic it took time to learn Dev - ops. | Dev-ops were very essential for continuous integration.
Analysis of PLP documents ( 19 nov 2019) | 2 | 2 | On time | PLP documents were Analysed and we went through the urs and other documents.
Revision Of Azure Concepts ( 19 nov 2019) | 1 | 1 | On time | Azure Concepts were Revisied red we went through the urs red other Concepts.
Learning the Agile and Scrum model ( 18 nov 2019) | 3 | 3 | On time | learnt about the basics of agile and scrum model
Creating Various PLP documents as URS, PRODUCT BACKLOG etc( 20 nov 2019) | 4 | 5 | As we needed to create 5 documents, so it took time. | Various documents were created Like urs etc.
| Sum - 21 hours | Sum - 22 hours
| Sum- 22.5 hrs | Sum- 26 hrs
Note on A23: Sinha, Ritwik:

## Pushpraj
Agile Task Board
Assigned To: | Pushpraj Kaushik
Use Case: | Use Case 1
Team: | Team D
Task | Actual No. of Hours Expected | Actual No. of Hours | Reason | Details
Inventory
Create WebApi Controller ( Solution) in Azure ( 16 nov 2019) | 1 | 2 | Learnt the Basic coding concepts about web api and and utilized on code. | Created webApi Controller and web Api configuration file containing object of Business layer with the required method.
Create the MVC project with Model view Controller with validation( 18 nov 2019) | 2 | 2 | On time | Created a MVC project Model view Controller with validation .
Consuming WebApi through MVC ( 21 nov 2019) | 1 | 1 | On time | Consumed WebApi through MVC method On all the CRUD operations.
Put up Database scripts on Azure Database SQL server ( 16 nov 2019) | 1 | 1 | On time | database scripts were executed and then put up on the azure database sql server.
Deploy the MVC project on Azure ( 21 Nov 2019) | 2 | 2.5 | As Azure is the difficult topic, It took time to learn the architecture. | It was a total new and useful concept to deploy our application on azure and learnt about the advantages.
Connect MVC project with Web Api( 20 nov 2019) | 2 | 2 | On time | Connection of web api and MVC was done and the project was running on local host.
learning of Dev-OPs( 20 nov 2019) | 2 | 2.5 | As it was a new topic it took time to learn Dev - ops. | Dev-ops were very essential for continuous integration.
Analysis of PLP documents ( 19 nov 2019) | 2 | 2 | On time | PLP documents were Analysed and we went through the urs and other documents.
Revision Of Azure Concepts ( 19 nov 2019) | 1 | 1 | On time | Azure Concepts were Revisied red we went through the urs red other Concepts.
Learning the Agile and Scrum model ( 18 nov 2019) | 3 | 3 | On time | learnt about the basics of agile and scrum model
Creating Various PLP documents as URS, PRODUCT BACKLOG etc( 20 nov 2019) | 4 | 5 | As we needed to create 5 documents, so it took time. | Various documents were created Like urs etc.